## Sheet1
Risk ID | Description | Likelihood | Impact | Score | Current Controls | Recommended Controls | Owner | Status
R1 | Model produces biased diet recommendations for certain groups (e.g. specific genders, ages, medical conditions) | 4 | 4 | 16 | Basic train/test split | Data audit; augment dataset; fairness tests; human review | Product Lead | Proposed
R2 | Storage of user images and health data without adequate encryption | 3 | 5 | 15 | Local storage, limited policy | Encryption at rest & transit; retention policy; consent capture | Engineering Lead | Proposed
R3 | Model drift causes diet suggestions to become less accurate over time | 3 | 3 | 9 | Periodic manual checks | Monitoring dashboard; retraining schedule; alerts | ML Engineer | Proposed
R4 | Lack of explainability reduces user trust and creates compliance concerns | 2 | 4 | 8 | No model card | Publish model card; simple user explanation; logging | PM / Compliance | Proposed